## Team Project Task Board
Start Date | Task | Description | Status | Due Date
2021-02-22 | Initial Meeting and Discussion | The team discussed the initial list of tools for the designing, development and deployment of data warehouse. The conceptual model was drafted. 1. Bottom Tier: database of the data warehouse; data is cleansed, transformed, and loaded into this layer using back-end tools. 2. Middle Tier /OLAP (ROLAP or MOLAP): mediator between the end-user and the database. 3. Top-Tier: front-end client layer, tools and API that you connect and get data out from the data warehouse; Query tools, reporting tools, managed query tools, Analysis tools and Data mining tools. Next Steps: - The team scheduled a call for Friday 2/26 at 3:30 pm to make the decision regarding the second dataset/unstructured dataset. - The team shared a google doc to document options for the unstructured dataset. - Ideas for the second dataset included: Zillow home prices data and web scraping Yeshiva’s website to enhance reporting. | Completed | 2021-02-28
2021-03-01 | Ideas for the second data set/Research ETL | Ideas for the second data set / unstructured data: · The team decided to use real estate and income unstructured data for the project · There data can be retrieved via API and/or by leveraging python libraries Design Phase: · The team decided that dividing the design of the database of the data warehouse into staging, performance and archive is a good idea.. Questions for the professor: · Do we need to move all the data through the pipeline or not? · Can we append a document file to our analytics directly from staging area, and does that meet the requirement for the unstructured data component for the project? *Daniel emailed the professor. Waiting to hear back. Items for next week: 1. Anna will put together a list of requirements /business logic and desired outputs 2. We are going to do research about ETL processes and come ready to start the conversation about it. 3. We are aiming to start building the philanthropy: donors data warehouse after our next meeting, scheduled for Friday March 5 at 3pm. | Completed | 2021-03-07
2021-03-08 | Start building the data warehouse | The team decided the unstructured data will be brought as a json into Jupyter into the dataframe and will be moved through the data pipeline as structured data. The team decided to start building the data warehouse. Below are the components each team member will be responsible for during the initial designing stage: · Anna – structured data: importing data into editor and performing transformation, loading data into dataframe and setting stage for the move of data through pipeline. · Daniel – unstructured data: importing data into editor and performing transformation, loading data into dataframe and setting stage for the move of data through pipeline. · Pujita – ETL: study approach for optimal data extraction and move into the analytics layer, understand destination for data, select ETL tools and coordinate systems setup/ setting up a physical environment. · Elham – ETL: study approach for optimal data extraction and move from editor into database, understand destination for data, select ETL tools and coordinate systems setup/ setting up physical environment. · Jesus – database architecture/support: coordinate blue blueprint and data modelling, develop star schema template, staging and archive templates. | Completed | 2021-03-14
2021-03-15 | The team discussed progress and to do list | The team discussed progress on individual tasks: Anna: Is working on the structure data and once that portion is ready will share it with the team. Pujita: Is working on the visualizations making sure it meets the requirements of the client. Anna will send the client requirements. Elham: Is working on choosing an ETL tool and building a data pipeline. Daniel: Is working on retrieving and transforming unstructured data. Jesus: Is building data warehouse databases. To do list: 1. Anna – send client requirements to Pujita, and structure dataframe to Jesus. 2. Pujita – build visualizations based on client’s requirements and reverse engineer visualizations to create custom queries. 3. Elham – chose ETL tool and coordinate with Daniel and Anna data pipeline strategy. 4. Daniel – coordinate with Elham and Anna insertion of unstructured data into data pipeline and send unstructured data dataframe to Jesus. 5. Jesus – setup databases and coordinate with all team members the overall data pipeline setup in and out of the databases. | Completed | 2021-03-21
2021-03-22 | Revised Architecture Diagram | Group Updates Daniel: He is working with the unstructured dataset, but still encountering runtime errors. New dataset might be needed. The goal is to have a robust dataset containing zip codes, median household income and median house price. Revised Architecture Diagram The team accepted the revised version, but OLAP cube might be removed from the process; it might not be needed. That decision will be made once the development team gets there. Alternatively, the team is evaluating the possibility of having customized queries directly querying into the database from Tableau instance. Development Schedule and *Considerations 1. GitHub Setup 3/29 @ 10 am EST - The team decided to incorporate GitHub to the overall development process. *Please come to the meeting with your GitHub desktop and website ready. 2. Extract Logic 3/30 @ 5:30 pm EST– The team will be evaluating the process of loading data into the data warehouse. *Please review M10 AWS Lambda videos – we might be incorporating that service from AWS into our overall design. 3. Transforming the data 3/31 @ 7:00 pm EST – The team will be wrapping up with the data wrangling. *The team will be using Jupyter Notebook as editor. 4. Moving data to database 4/1 @ 10 am EST – The team will be working on moving the data from dataframe to S3 and MYSQL. *Please make sure your AWS and workbench are working before the meeting. 5. Moving data from database to reporting layer 4/2 @ 10:30 am EST – The team will be working on creating the MYSQL instance on Tableau connecting database and importing customized queries. *Please make sure your Tableau desktop and online versions are set up. Next Steps: - The team will be putting the dates on the calendar for the remaining steps of the development process on 4/2. | Completed | 2021-03-28
2021-03-29 | Discussed having two dashboards | We discussed having two dashboards: one for EDA and one for donation insights. Some donation insights include: -Zip codes by number of donors and by dollar amounts -Relationship between average home value and average gift from the same zip code -Relationship between average income and average gift from the same zip code -Giving loyalty patterns such as are major gift ($50K+) donors more loyal? Loyalty can be defined as giving 3, 4 or 5 fiscal years in a row. Even some counts on how many donors give 3, 4 or 5 years would be great. -How much can YU expect to bring in this fiscal year based on previous fiscal years? The colleges labeled Cardozo, RIETS, and High Schools could each be treated as separate entities if no clear patterns are emerge from our data. Each of those schools are different and may have different donor bases than our undergraduate schools. If we don’t have time, we will not worry about this. We are flexible on the insights listed above and will also work backwards to form new questions if we see interesting trends in the data. Action Items: Pujita is comfortable getting started with the data she has received from me and Daniel. Elham is working on the star schema and will send it to the group when she is finished. We will have 8 tables: fact table, person, date, donation, location, designation, school, and census data (for median home value and median income value). | Completed | 2021-04-04
2021-04-05 | Operation’s schema diagram-Populate the operations database | To do: 1. Script: Operations Database 2. Script: Populate Operations Database from Staging Database 3. Dashboard: (1) Create MySQL instance, (2) create summary dashboard, and (3) create operations dashboard. 4. Documentation: (1) Project Description, (2) User Manual, and (3) Final Presentation. Next Steps: 1. Anna will review Elham’s operation’s schema diagram and will send it back to Elham so she can write the script. 2. Daniel will create the script to populate the operations database from the staging database. 3. Pujita is going to create V1 of Dashboards (summary and operations). Timeline: The team agreed on completing all the items above before April 23rd; on that day the team will have V1 completed and working. Next Meeting: 1. Catch up meeting to follow up on progress on Monday 4/12/21 at 11 am. On that day the next catch-up meeting will be scheduled. 2. Deadline for completion of V1: Friday April 23rd at 3 pm EST. | Completed | 2021-04-11
2021-04-12 | scripts for creating database and loading data into database | · Elham shared V1 of scripts for creating database and loading data into database from staging. · The team decided to add a shared key on both, the donor dimension, and the donation dimension. · Jesus is going to update the scripts and send them to the team for a second look. He will also be writing the script for dropping the staging table. · Daniel is going to update the zip code dataset by year and share with the team. · Pujita – is going to keep working on the 2 dashboards. *Development of V1 deadline: Friday 4/16/21 *Next Meeting: Thursday 4/15/21 at 1 pm. | Completed | 2021-04-18
2021-04-19 | Schema and Scripts Update | Schema Update: - The team decided that dim location will be hosted on a separate database on MySQL to ensure consistency on all the data across the rpt database on updates. - The analytics regarding zip code, median income and home value will be handled on the visualization layer. To do list: A. Schema and Scripts Update - Elham and Daniel will be working on updating the scripts (SQL and Python) to reflect changes made on the schema and will finish the integration of existing code into the pipeline to update the database hosting the home prices and median income by zip code (“location/stats” on-boarding file). A meeting is scheduled for 4/24/21 to work on the development. B. Documentation - Bus matrix - Anna - Basic use cases/user stories for analytics – Anna and Puji - Dimensional Model Matrix with ETL instructions – Anna: Dim mod matrix / Jesus and Daniel, Elham ETL instructions - Conceptual, Logical, and Physical Data Model - Anna - Architecture diagram with network information – Daniel and Jesus - Data Dictionary (Dataedo for formatting) – Daniel - High level agile project plan – Each one will write a description of their individual components and Daniel will map the timeline of project development based on meeting minutes. C. Testing - Each team member will set up the infrastructure in their environment and conduct initial testing before meeting with the professor. Tentative schedule to wrap up project: - Scripts/pipeline will be completed by 4/27 - Meeting with the professor to give updates and receive feedback 4/28 - Updates and testing period after feedback from professor last day 5/3 - Documentation completion last day 5/7 - Final presentation to be completed and Github documentation ready for submission by 5/10 - Final presentation rehearsal 5/11 - Presentation and delivery of the entirety of the project on 5/12 | Completed | 2021-04-25
2021-04-26 | Pipeline nearing completion. | Everyone: The team will be sending Daniel all the documentation on the same email trace. ALL documentation must be in Daniel’s hands before 5/7 morning. Daniel: Daniel will complete the documentation and Github site before our rehearsal on 5/10. Pujita: Pujita will be finishing the dashboards and setting up the MySQL interface. Pujita will be working with Anna to complete the Basic use cases and stories for analytics. If needed, some customized queries will be developed. Anna: Anna will complete the bus matrix, basic use cases/ user stories for analytics, dimensional model matrix and the Conceptual, Logical, and Physical Data Model. Jesus: He will be putting together the first draft of the architecture diagram with Daniel. Elham: She will be available in the case a team member needs help meeting the deadlines. Important Dates Wed 5/5: Jesus and Pujita will finish mapping the python scripts. Time: 1 pm Thu 5/6: Daniel and Jesus will be working on the Network Diagram. Time 11:15 am Thu 5/6: Everyone - Setup and Testing. Time 11:30 am Fri 5/7: Everyone – Documentation last looks and Second Dashboard Review. Time 12 pm Sun 5/9: Everyone – The team will be building the final presentation. Time 11 am Mon 5/10: Everyone – Presentation Rehearsal. Time 6 pm | Completed | 2021-05-02
2021-05-03 | Setting up all Documentation | To do: 1. Jesus shared the “Read me” on google docs. Everyone will go and make the final updates. 2. Anna and Pujita will be working over the weekend on finishing the dashboard and writing the “Basic Use and Case for Analytics” file. 3. Anna will be completing the “Dimensional model matrix”. 4. Daniel will be writing the “High level project plan” and will be working with the folder structure for the Github repository. Github Repository: jaynuel/donors_dw Folder Structure: 1. Folder Name: Scripts 1.1 Folder Name: SQL 1.2 Folder Name: Python 2. Folder Name: Documentation 2.1 Folder Name: Project Management 2.2 Folder Name: Databases 2.2A Folder Name: Images 2.3 Folder Name: ETL 2.4 Folder Name: Analytics (Tableau) 3. Raw Datasets (Folder already in repository) Deadline for completion of items above: Sunday 5/9 Next Meetings: - Sat 5/8 at 12 pm: Pujita and Anna / dashboard and analytics (cause use) - Sun 5/9 at 11 am: All – Last updates and Presentation development - Mon 5/10 at 6 pm: Final Presentation Rehearsal - Wed 5/12 at 8:30 pm: Final Presentation | Completed | 2021-05-09
2021-05-10 | Final Meeting For Presentation Rehearsal | Presentation Rehearsal | Completed | 2021-05-12